## Sheet1
Trade Area | Landlord | Size | Asking Terms | Date LOI Sent/Accepted | Status of Lease | Proposed Terms (Market) | CAM/Ins | Taxes | TI Allowance | Delivery Date | Projected Opening | Major Issues | Current Status | Next Step
Alexandria, VA | JBG Retail | 3,000 sf | $50 psf |  |  | $50.00 psf | 3 | 3 | N/A | 2012-01-01 | mid 2012 |  | Lease | We will need to go through the Exception process - Terry and Don to set-up call with lawyer to better understand potentail cost and time line.
Manassas, VA | Seneca Development | 3,200 sf | $50 psf |  |  | $46.50 psf | 1 | 2.75 | N/A | 2010-12-01 | 2011-03-01 |  | Lease | starting const 4/14/11
Olney, MD | Streetsense | 3,600 sf | $40 psf |  |  | $40.00 psf | 6 | 3 | N/A | immed. | 2011-04-27 |  | Lease | opening scheduled 4/27/11
Seven Corners | Regency | 2,694 sf | $50 psf |  |  | $45.00 psf |  |  | N/A | 2011-06-01 | 4Q11 |  | Lease | delivery scheduled July 2011
Germantown, MD | Minkoff | 3,200 sf | $45 psf |  |  | $40.00 psf | 4 | 3 | none | 4Q11 | early 2012 |  | Lease | Signed Lease returned from LL
Greenbriar, VA | Regency | 3,000 sf | $35-45 psf |  |  | 45.00 psf | 6 |  | WL | 2011-11-01 | 2Q12 |  | LOI | LL agreed with LOI and has requested Lease which is expected next week, we need "As-Builds"
Baileys Cross Roads | Levin Management | 3,000 sf | $50 psf |  |  | $43.00 psf |  |  | N/A | 2012-05-01 | late 2012 |  | LOI | waiting on LL reply
Sterling, VA | Kimco | 3,000sf | $ 50 psf |  |  | $40 psf |  |  | $135K | 3Q11 | 1Q12 |  | LOI | signed LOI
Annapolis | Greenberg/Gibbons | 3600sf | $50psf |  |  | $40psf | 9.56 | 3.15 | $225K | 2012-06-01 | 2012-09-01 |  | LOI | Signed LOI
Annapolis - Bank Site | [13 empty] | James to re-vist the Bank Deal for us
Silver Spring, MD | Peterson | 3400sf | $30psf |  |  | $52.50 psf | 10.43 | 2.53 | N/A | 4Q 2011 | 2Q2012 | Baja Fresh | LOI | singed LOI
Arundel Mills | Simon | 6000sf | $37psf |  |  | $29psf |  |  | N/A | 2011-10-01 | 2Q2012 |  | LOI | Tenant offer being considered by LL & M&T
Stafford, VA | Kodiak | 2,500sf | $26 psf |  |  | $26 psf | 4 | 2.1 | $10 psf | 2011-07-01 | 1Q2012 |  | LOI | Need to review on next site review
Waldorf, MD | Madison | 3,025 sf | [7 empty] | 4Q2011 | 2Q2012 | Blockbuster |  | Blockbuster site getting LOI
Lexington Park, MD | Segall Development | 3,500sf | $36 psf |  |  | $36 psf | 2.55 | 1.5 | $50K+WL | 2012-06-01 | 2012-10-01 |  | LOI | Need to review on next site review
Burke, VA | BTCLLC | 3,116 sf | $ 45 psf |  |  | $35 psf | 2.98 | 2 | $15 psf |  |  |  | LOI | Need to review on next site review
Bowie, MD
Arlington, VA
Rockville, MD
Leesburg, VA
Kingstowne/Springfield, VA | [13 empty] | Chipotle excludes us
Columbia, MD
Gaithersburg, MD | [13 empty] | find traditional
Herndon, VA
Fredericksburg, VA
Van Dorn, VA | Edens & Avant and Minkoff | 2,880 sf | 45 psf |  |  | $34.00 psf | 2.16 | 3 | N/A | early 2011 | mid 2011 |  | LOI | at Lease
College Park, MD | Jim McGinnis | 3-4,000 sf | $55 psf |  |  | $40.00 psf | 5 | 3 | N/A | late 2010 | early 2012 | site plan approval | LOI | need to finalize LOI
Potomac Mills, VA | Kimco | 5,200sf | $175,000/yr GL |  |  | $125,000/yr GL | 1.81 | 2.16 | site work | late 2011 | early 2012 | Taco Bell Coven |  | restrictive covenant
Frederick, MD | Whitestar | 2,616sf | $38psf |  |  | $30.00psf | 5 | 2.69 | $25psf | immed | 2Q11 | parking | LOI | deal did not work
Annapolis, MD | Tire store and bank | 3-4,000sf | $35 and $16 psf | [8 empty] | redevelopment and retrofit | LOI | owner went with other deal
Sterling, VA | Combined Properties | 3,600-4,700sf | $35psf | [10 empty] | did not like parking/center
Laurel, MD | 1st Allied Corp | 4800sf |  |  |  | $30psf | [7 empty] | did not like access
Bowie, MD | Next Realty | 3,200sf | 45 | 2007-07-01 |  | $38psf | 4.8 | 3 | N/A | early 2011 | mid 2011 | 7-11 Renewal Opt |  | renewed existing tenant
Fairfax, VA | J. Donegan | 2,800sf | $50psf |  |  | $42psf | 5 | 5 | N/A | 2010-05-01 | 2010-09-01 | N/A | Lease | not enough parking
N. Arlington, VA | Combined Properties | 2,800sf FS | $150,000/yr GL |  |  | $135,000/yr GL |  |  | site work | 2011-06-01 | late 2011 | site plan approval | LOI | space too small